## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Dunia Blogger | Judul Besar | Task 1.1 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 2 | Task 2.1 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 3 | Task 3.1 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 4 | Task 4.1 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 5 | Task 5.1 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 6 | Task 6.1 | 4 | 4 | 2 | 2 | 0 | 0 | 0
Dunia Blogger | Slide 7 | Task 7.1 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 8 | Task 8.1 | 4 | 4 | 2 | 2 | 0 | 0 | 0 |  | 0
Dunia Blogger | Slide 9 | Task 9.1 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 |  | 0
Dunia Blogger | Slide 10 | Task 10.1 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0
Dunia Blogger | Slide 11 | Task 11.1 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 12 | Task 12.1 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 13 | Task 13.1 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 14 | Task 14.1 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Slide 15 | Task 15.1 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Styling | Task 16.1 | 10 | 10 | 9 | 9 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Dunia Blogger | Bux Fixing | Task 17.1 | 10 | 10 | 9 | 9 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 80 | 73.3333 | 66.6667 | 60 | 53.3333 | 46.6667 | 40 | 33.3333 | 26.6667 | 20 | 13.3333 | 6.6667 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 80 | 74 | 60 | 46 | 30 | 22 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered